## Team Backlog
Team Backlog
Task Name | Assignee | Task Status | Expected Time to Finish (Hrs) | Actual Time to Finish (Hrs)
Design
High Level Design
Modules' Description | All Team | Done | 1 | 1
Drivers' Documentation | All Team | Done | 1 | 1
Low Level Design
Functions' Flowchart | All Team | Done | 2 | 2
Summary
Document File | Hossam | Done | 1 | 2
Implementation
MCAL Module
GPIO Driver | Alaa | Done | 0.5 | 0.5
GPT Driver | Hossam | Done | 0.5 | 0.5
HAL Module
BTN Driver | Sarah | Done | 1 | 1
DCM Driver | Ahmed | Done | 1 | 1
Delay Driver | Hossam | Done | 1 | 1.5
PWM Driver | Alaa | Done | 0.5 | 0.5
LED Driver | Hossam | Done | 0.5 | 0.5
APP Module
App Driver | Alaa & Hossam | Done | 3 | 5
Testing
Documentation
Test Protocol Excel Sheet | All Team | Done | 1 | 1
Unit Testing
Test MCAL | All Team | Done | 2 | 2
Test HAL | All Team | Done | 1 | 1
System Testing
Test APP | All Team | Done | 2 | 7
Final Requirements Review | All Team | Done | 1 | 2
Video
Video Recording | All Team | Done | 2 | 3
Video Editing / Upload | Hossam | Done | 1 | 1

## Test Protocol
Test Protocol
Test Case ID | Test Case Description | Test Case Steps | Expected Result | Actual Result | Pass/Fail
APP Module
App Testing
TC_APP_001 | Normal Application Flow | 1. Flash the program hex file 2. Press Reset Switch 3. Press Start Button | 1. The car starts initially from 0 speed 2. When PB1 is pressed, the car will move forward after 1 second 3. The car will move forward to create the longest side of the rectangle for 3 seconds with 50% of its maximum speed 4. After finishing the first longest side the car will stop for 0.5 seconds, rotate 90 degrees to the right, and stop for 0.5 second 5. The car will move to create the short side of the rectangle at 30% of its speed for 2 seconds 6. After finishing the shortest side, the car will stop for 0.5 seconds, rotate 90 degrees to the right, and stop for 0.5 second 7. Steps 3 to 6 will be repeated infinitely until you press the stop button (PB2) 8. PB2 acts as a sudden break, and it has the highest priority 9. LEDs Operations 1. LED1: On means moving forward on the long side 2. LED2: On means moving forward on the short side 3. LED3: On means stop 4. LED4: On means Rotating | Matches Expected Result | Pass
TC_APP_002 | Stop Button Press | Press the stop button at any state during the program execution | The car stops immediately and the stop LED turns on. | Matches Expected Result | Pass